| PART I – SUMMARY OF ACTION PLAN |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | Risk Indicator (select from pull down menu) | Initial Risk Quantifier (type in event trigger) | Summary of Root Cause (escribe the underlying issues) | Risk Mitigation Steps (list Action Plan Steps) | Action Plan Goal(s) (final goal of Action Plan) | Anticipated End Date (not to Exceed 1 Year) |
| 1 | Financial risk metric of Operator (DSCR) | DSCR 0.70 | Facility currently has 10 vacant beds due to newer facilities in the market area. Due to holidays/winter season, admissions have slightly slowed, which has impacted revenue. 80% Beds Filled. | - Increase Marketing Efforts - Update curb appeal of property - Improve relationship with local hospitals to increase referrals - Decrease reliance on contracted staff/staffing agency - Explore cost saving opportunities | DSCR of 1.0 or more | 12/31/2021 |
| 2 | REAC inspection | 3 Failed REAC Inspections 33c - Sept 2017 56c - Sept. 2018 55c - Oct 2019 | Official Maintenance Plan and Procedures (MPP) not followed. | - Administrator to review and certify reviewing MPP - Training for Maintenance Staff - Staff to do 100% walkthrough of property and prepare work orders for repair/replacement items - Repairs/Replacements to be made prior to REAC Inspection - Borrower to submit Owner’s Certification required by NOV | REAC Inspection Score of 60+ | 12/31/2021 |
| 3 | State inspections | Open H tag | Medication administration issues and lack of proper staff training. | - Director of Nursing to review and improve Infection Control protocol - Administrator to provide staff training | Substantial Compliance | 12/31/2021 |
| Frequency of HUD Reporting: Quarterly FIRST ACTION PLAN PROGRESS REPORT DUE: 3/31/2021 |  |  |  |  |  |  |

| PART II – MONITORING OF ACTION PLAN |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Item | Action Plan Goal | Anticipated End Date | Action Plan Progress as of: 3/31/2021 | Action Plan Progress as of: 6/30/2021 | Action Plan Progress as of: 9/30/2021 | Action Plan Progress as of: 12/31/2021 |
| 1 | DSCR of 1.0 or more | 12/31/2021 | Progress Report (provide quantifiable details): DSCR increased to 0.80; beds are 41/50 filled (82%); advertised in new local paper, landscaping project underway. Scheduling open house with local hospitals shortly. On Target? Yes - On Target | Progress Report (provide quantifiable details): DSCR 0.83; 42/50 Beds filled (84%); open house with hospitals was successful; found a way to reduce administrative expenses by 20%. On Target? Yes - On Target | Progress Report (provide quantifiable details): DSCR 0.96; 45/50 Beds filled (90%); fully staffed, no longer relying on temp. agencies. Continuing to work with hospitals on referrals. On Target? Yes - On Target | Progress Report (provide quantifiable details): DSCR 1.05; 49/50 Beds filled (98%). On Target? Yes - Action Plan Complete - Completion Date: 12/25/2021 |
| 2 | REAC Inspection Score of 60+ | 12/31/2021 | Progress Report (provide quantifiable details): REAC Not Scheduled Administrator has certified reviewing MPP. 100% Inspection Walkthrough scheduled. On Target? Yes - On Target | Progress Report (provide quantifiable details): Loss of staff resulted in walk-through not occurring. On Target? No-See Lender Comments below | Progress Report (provide quantifiable details): 100% inspection occurred. Back on target. REAC Scheduled for 12/01/2021; Staff continuing monthly walkthroughs to keep property maintained. On Target? Yes - On Target | Progress Report (provide quantifiable details): REAC Score 62 on 12/31/2021 On Target? Yes - Action Plan Complete - Completion Date:12/31/2021 |
| 3 | Open H tag | 12/31/2021 | Progress Report (provide quantifiable details): Infection control procedures updated and all staff trained on new protocol. Property has provided Lender with letter noting they are back in substantial compliance. On Target? Yes - Action Plan Complete - Completion Date: 3/20/2021 |  |  |  |
|  |  |  | LENDER COMMENTS: N/A | LENDER COMMENTS: Held call on 5/15/2021 and the Operator confirmed staffing issues are resolved and plan is back on track. | LENDER COMMENTS: N/A | LENDER COMMENTS: N/A |
| Frequency of HUD Reporting: Quarterly FIRST ACTION PLAN PROGRESS REPORT DUE: 3/31/2021 |  |  |  |