## Sheet1
Level 1 | Level 2 | Level 3
1 COTS/GOTS | 1.1 Pre-PPM Activities | 1.1.1 Establish Project Sponsor
1.1.2 Determine IT Project Manager
1.1.3 Conduct Program/Project Management
1.1.4 Milestone: Project Approved
| 1.2 Initiation Phase | 1.2.1 Complete Project Initiation Form (PIF)
1.2.2 Milestone: Project Commencement Notification Completed
1.2.3 Establish Integrated Project Team (IPT)
1.2.4 Conduct Project Kickoff Meeting
1.2.5 Develop Project Charter
1.2.6 Milestone: Project Charter Completed
1.2.7 Develop Initial Detailed Work Breakdown Structure for Project Type
1.2.8 Develop Initial Detailed Project Schedule (Minimum through Planning Phase)
1.2.9 Update/Validate Business Case and Life Cycle Cost Estimate (from budget formulation process)
1.2.10 Update/Validate Projected Project or Solution Benefits (from budget formulation process)
1.2.11 Assess Preliminary Procurement Support Needed
1.2.12 Develop Procurement Management Approach and Plan (if applicable)
1.2.13 Finalize Artifacts and Obtain Necessary Signoffs/Signatures
1.2.14 Milestone: Procurement/Acquisition Approach Defined
1.2.15 Conduct Project Validation Review Control Gate
1.2.16 Conduct Program/Project Management
1.2.17 Milestone: Project Initiated
| 1.3 Planning Phase | 1.3.1 Procure Resources per the Acquisition Strategy (for Requirements or Entire Project)
1.3.2 Milestone: Contracts Signed/ Task Order Issued (Planning Phase Support)
1.3.3 Develop Project Tailoring Agreement (PTA)
1.3.4 Mobilize Resources (People)
1.3.5 Re-Evaluate Project Timeline and Update Project Schedule
1.3.6 Develop Project Management Approach and Plan
1.3.7 Develop the Concept of Operations (CONOPS) (at the Initiative or Program Level)
1.3.8 Identify Project Business and Functional Requirements
1.3.9 Milestone: Project Requirements Defined
1.3.10 Develop Solution Architecture
1.3.11 Milestone: Solution Architecture Completed
1.3.12 Develop Risk Management Plan and Risk Log
1.3.13 Develop Quality Assurance Approach and Plan
1.3.14 Develop Communications Management Plan
1.3.15 Determine Project Approach for Independent Verification and Validation (IV&V)
1.3.16 Develop Security and Privacy Documentation
1.3.17 Update Project Schedule from Initiation Phase
1.3.18 Finalize Artifacts and Obtain Necessary Signoffs/Signatures
1.3.19 Conduct Project Baseline Review Control Gate
1.3.20 Conduct Program/Project Management
1.3.21 Conduct IV&V Activities
1.3.22 Milestone: Project Planning Completed
| 1.4 Execution & Control Phase | 1.4.1 Procure Resources per the Acquisition Strategy (Design/Installation/Configuration/Development and/or Solution (if applicable)
1.4.2 Monitor and Control Quality Assurance Activities
1.4.3 Develop Solution Technical Design and Define Interfaces
1.4.4 Milestone: Solution Technical Design Completed
1.4.5 Execute Change Management Process
1.4.6 Plan the Implementation and Release Approach
1.4.7 Determine Testing Strategy
1.4.8 Create the Data Conversion Strategy (if applicable)
1.4.9 Configure the Development, Testing & Training Environments (if applicable)
1.4.10 Configure and Unit Test Software
1.4.11 Conduct User Acceptance Testing (UAT)
1.4.12 Milestone: Development/Configuration and Testing Completed
1.4.13 Develop Training Strategy and Plan
1.4.14 Develop End User Training Content
1.4.15 Conduct Training for End Users
1.4.16 Create Operations and Maintenance Documentation (O&M and User)
1.4.17 Create and/or Update Security Artifacts
1.4.18 Obtain Authorization to Operate (ATO)
1.4.19 Install the Solution/ Submit the Software Release Request (HARTS)
1.4.20 Milestone: Production Environment Ready
1.4.21 Conduct Project Operational Readiness Review Control Gate (Repeat as Necessary)
1.4.22 Release Solution in Production for Official Go-Live
1.4.23 Conduct Program/Project Management
1.4.24 Conduct IV&V Activities
1.4.25 Milestone: Go-Live/Solution in Production for End Users/Customer Base
| 1.5 Close Out Phase | 1.5.1 Conduct Post Deployment/Warranty Support (if applicable)
1.5.2 Handoff Solution to Operations & Maintenance for Support
1.5.3 Conduct Post-Deployment Review
1.5.4 Conduct Project Close Out Activities
1.5.5 Prepare Project Completion Report
1.5.6 Conduct Project Close Out Review Control Gate
1.5.7 Milestone: Project Close Out Completed
1.5.8 Provide System Documentation to HUD IT Operations
1.5.9 Conduct Program/Project Management
1.5.10 Conduct IV&V Activities
1.5.11 Milestone: Project Finished