## Sheet1
Level 1 | Level 2 | Level 3
1 Decommission | 1.1 Pre-PPM Activities | 1.1.1 Complete Annual Operational Assessment
1.1.2 Conduct Program/Project Management
1.1.3 Milestone: Project Approved
| 1.2 Initiation Phase | 1.2.1 Establish Integrated Project Team (IPT)
1.2.2 Identify System Interface
1.2.3 Define Database Dependencies
1.2.4 Develop Initial Project Schedule
1.2.5 Update System Life Cycle Cost Estimate
1.2.6 Conduct Program/Project Management
1.2.7 Milestone: Project Initiated
| 1.3 Planning Phase | 1.3.1 Perform Migration Planning
1.3.2 Plan for Decommissioning
1.3.3 Milestone: Project Requirements Defined
1.3.4 Conduct Program/Project Management
1.3.5 Conduct Project Baseline Review Control Gate
1.3.6 Milestone: Project Planning Completed
| 1.4 Execution & Control Phase | 1.4.1 Complete DPPD Application System Retirement Request
1.4.2 Complete IAS Inactivation Form
1.4.3 Perform Migration Activities
1.4.4 Ensure Interfaces Addressed for Live Systems
1.4.5 Conduct SORN Deletion
1.4.6 Perform Decommissioning Activities
1.4.7 Conduct Program/Project Management
1.4.8. Milestone: Asset Decommissioned
| 1.5 Close Out Phase | 1.5.1 Complete Post-Decommissioning Report
1.5.2 Conduct Program/Project Management
1.5.3 Project Close Out Completed
1.5.4 Milestone: Project Finished